## Sheet2
Task and its short description	15.02–15.03	15.03–15.04	15.04–15.05	15.05–15.06	15.06–15.07	15.07–15.08
T1.1: Research on social behaviour DL concepts
T1.2: Research on game difficulty DL adaptation concepts
T2.1: Selection of social behaviour DL architectures
T2.2: Selection of the suitable datasets
T2.3: Selection of the best performing DL model
T3.1: Adaptation of the chosen DL architecture
T3.2: Initial training and evaluation of the adapted architecture
T4.1: Preparation of the experimentation setup
T4.2: Real-life evaluation of the DL model
T5.1: Combining reports from the previous deliverables
T5.2: Detailed description of the real-world experimentation
T5.3: Creation of the proper visualisations of the evaluation results
T5.4: Iterative corrections with the supervisors

M2
M3

M1