## Sheet2
Task and its short description	01.03–01.04	01.04–01.05	01.05–01.06	01.06–01.07	01.07–01.08	01.08–01.09
T1.1: Research on social behaviour DL concepts
T1.2: Research on game difficulty DL adaptation concepts
T2.1: Selection of social behaviour DL architectures
T2.2: Selection of the suitable datasets
T2.3: Selection of the best performing DL model
T3.1: Adaptation of the chosen DL architecture
T3.2: Initial training and evaluation of the adapted architecture
T4.1: Preparation of the experimentation setup
T4.2: Real-life evaluation of the DL model
T5.1: Combining reports from the previous deliverables
T5.2: Detailed description of the real-world experimentation
T5.3: Creation of the proper visualisations of the evaluation results
T5.4: Iterative corrections with the supervisors

M2
M3

M1