## Sheet2
Task and its short description | 15.02–15.03 | 15.03–15.04 | 15.04–15.05 | 15.05–15.06 | 15.06–15.07 | 15.07–15.08
T1.1: Research on social behaviour DL concepts
T1.2: Research on game difficulty DL adaptation concepts
T2.1: Selection of social behaviour DL architectures
T2.2: Selection of the suitable datasets
T2.3: Selection of the best performing model
T3.1: Adaptation of the chosen DL architecture
T3.2: Initial training and evaluation of the adapted architecture
T4.1: Preparation of the experimentation setup
T4.2: Real-life evaluation of the DL model
T5.1: Merge of the reports from the previous deliverables
T5.2: Detailed description of the real-world experimentation
T5.3: Creation of the proper visualisations of the evaluation data
T5.4: Iterative corrections with the supervisors
M2
M3
M1